## Requirements
Requirements
Terms:
- appointments for lectures, exercise classes and exams, lecturer
- block appointments
From description
Organizing appointments
- Graphical tool
- Visualizes the current schedule
- Allow to change it by dragging events to a new place: drag-and-drop
- Two planning modes
1. Lectures and exercise classes are scheduled for the whole lecture period
- weekly
- bi-weekly
- block events
- block events may take place outside the normal lecture period.
- One course can have multiple lecture and exercise classes per week.
2. Exams are spread over a period of three or two weeks and fall into two examination periods.
- One class can only have one exam per exam period;
- Courses with oral exams may or may not be included in the planning.
- Create new appointment
- Specify and edit information
- Lecturer
- (Title?)
- Kind of event
- Room (optional?)
- Expected number of participants (optional?)
Storage & Retrieval
- save schedule automatically
- download the current planning
- There may be the option to define a schema.
- upload schedule and activate it, for example, to revert to a previous planning status
- upload initial schedule
- schedule of previous semesters: Question: In what form available?
- consider false and missing values
- download the current planning in the form of a human readable list (?)
- that can be used as instructions for booking the appointments in the course catalog
- and reserving corresponding rooms.
- In this list, it should be visible, which appointments have been changed compared to the initial planning.
Conflicts
- Consider conflicts between lectures
- analyze study plans
- derive dependencies
- courses suggested to be studied in the same semester of any of the programs are in strong conflict
- courses in adjacent study year have a weak conflict
- check for conflicts in the planning
- other kinds of conflicts
- overlapping lectures by the same instructor
- lectures in the same room
- also consider bi-weekly and block events
- check overlap of block events with exam period
- (more?)
- Highlight possible conflicts
- mark conflicts
Optional requirements
• When dragging an event, the planner may highlight possible target time slots, where no conflict would be detected.
• The planner should have a read-only mode, in which a schedule is only displayed but cannot be edited;
- in this mode, the schedule information may be read from a file
that is (manually) uploaded in the Git repository of the Gitlab Page project.
• It should bepossible to apply filters to the view of the schedule planner, e.g., by instructor or by study program.
- Select lectures to include in schedule
• The schedule (possibly with applied filters) should be exported to a PDF.
• The planner should offer possible choices of rooms for events based on the expected number of participants and room-planning for overlapping events.
• It should also be possible to include a list of possible rooms instead of just one.
• When the appointments of basic courses are moved, a warning should be displayed, because these appointments should usually not change.
Own Ideas:
- Also make a two-week view or as many weeks as you like.
- Let the calendar look nice.
- The file shall be editable
Note on A13: Michael Gersom Gilge: "Could be done depending on the period where one is operating"

## Tech
General technical conditions
- Web page
- React
- Material UI
- The current planning should be stored in the HTML 5 local storage
- such that the status is not lost if the web page is closed accidentally
- and planning can be continued when the page is opened again.
- Browser based (without server)
- Typescript or Javascript
- Node Package Manager for the build configuration
- Host as Gitlab Page

## Time Plan
Time Plan
Until 2nd Milestone
- Inform about Git
- Inform about React and all the other technical necessities
- Experiment generating a web site
- Implement calendar view | Minimal viable product
- Implement drag and drop of events
- Download schedule
- Upload schedule
Until 3rd Milestone
Full functionality of Storage & Retrieval
Full functionality of Organizing events
Until 4th Milestone
- Calculation of Conflics
- Highlighting Conflicts
Acceptance Meeting
- Make final report from partly reports.

## Cost estimation & Schedule
Line | Prioritiy | Requirement | Estimated hours | Alexander | Michael | Mostafa | ∑ Hours | Weeks | Date | Start date
41 | 1 | Using Gitlab Page as host. | 24 | 8 | 8 | 8 | 24 | 0.57143 | 2024-06-02 | 2024-05-15
39 | 2 | Using Node Package Manager for the build configuration. | 20 | 8 | 8 | 4 | 44 | 1.0476 | 2024-06-05 08:00
33 | 3 | Using React. | 20 | 8 | 8 | 4 | 64 | 1.5238 | 2024-06-08 16:00
35 | 4 | Using Material UI. | 20 | 8 | 8 | 4 | 84 | 2 | 2024-06-12
37 | 5 | The current planning should be stored in the HTML 5 local storage such that the status is not lost if the web page is closed accidentally and planning can be continued when the page is opened again. | 24 | 8 | 8 | 8 | 108 | 2.5714 | 2024-06-16
31 | 6 | Using Typescript or Javascript. | 20 | 8 | 8 | 4 | 128 | 3.0476 | 2024-06-19 08:00
29 | 7 | The application shall be browser based (without a server). | 24 | 8 | 8 | 8 | 152 | 3.619 | 2024-06-23 08:00
36 | 7 | CSS | 16 | 6 | 6 | 4 | 168 | 4 | 2024-06-26
3 | 2100 | 2.0.0 Landing Page | 20 |  |  |  | 188 | 4.4762 | 2024-06-29 08:00
11 | 2210 | 2.3.1 Creating an Appointment via button | 20 |  |  |  | 208 | 4.9524 | 2024-07-02 16:00
13 | 2220 | 2.3.2 Creating an Appointment via double click | 20 |  |  |  | 228 | 5.4286 | 2024-07-06
15 | 2270 | 2.3.3 Editing Appointment | 15 |  |  |  | 243 | 5.7857 | 2024-07-08 12:00
17 | 2310 | 2.3.4 Moving Appointment per Drag & Drop | 20 |  |  |  | 263 | 6.2619 | 2024-07-11 20:00
19 | 2410 | 2.3.5 Deleting Appointment | 12 |  |  |  | 275 | 6.5476 | 2024-07-13 20:00
21 | 2440 | 2.3.6 Deleting All Appointments | 10 |  |  |  | 285 | 6.7857 | 2024-07-15 12:00
9 | 2510 | 2.2.1 Downloading File | 20 |  |  |  | 305 | 7.2619 | 2024-07-18 20:00
5 | 2610 | 2.1.1 Uploading File per Drag & Drop | 30 |  |  |  | 335 | 7.9762 | 2024-07-23 20:00
7 | 2620 | 2.1.2 Uploading File per File Selection | 20 | after 2.1.1 |  |  | 355 | 8.4524 | 2024-07-27 04:00 | 2nd milestone
25 | 2900 | 2.100.0 It should be nice and intuitive | 10 |  |  |  | 365 | 8.6905 | 2024-07-28 20:00 | 2024-06-27
| 3010 | 3.0.0 Landing Page / Welcome View | 4 |  |  |  | 369 | 8.7857 | 2024-07-29 12:00
| 3110 | 3.0.1 Start from Scratch | 4 |  |  |  | 373 | 8.881 | 2024-07-30 04:00
| 3150 | 3.0.2 Return to Welcome View | 4 |  |  |  | 377 | 8.9762 | 2024-07-30 20:00
| 3220 | 3.3.1 Create Course | 16 |  |  |  | 393 | 9.3571 | 2024-08-02 12:00
| 3310 | 3.1.1 Uploading File per Drag & Drop | 10 |  |  |  | 403 | 9.5952 | 2024-08-04 04:00
| 3320 | 3.1.2 Uploading File per File Selection | 10 |  |  |  | 413 | 9.8333 | 2024-08-05 20:00
| 3360 | 3.1.3 Uploading initial schedule | 25 |  |  |  | 438 | 10.4286 | 2024-08-10
| 3410 | 3.2.1 Downloading File | 20 |  |  |  | 458 | 10.9048 | 2024-08-13 08:00
| 3420 | 3.2.2 Human Readable Form | 20 |  |  |  | 478 | 11.381 | 2024-08-16 16:00
| 3510 | 3.2.20 Saving Calendar | 16 |  |  |  | 494 | 11.7619 | 2024-08-19 08:00
| 3520 | 3.2.21 Choosing Auto Save Folder | 10 |  |  |  | 504 | 12 | 2024-08-21
| 3530 | 3.2.22 Delete Old Auto Saved Files | 6 |  |  |  | 510 | 12.1429 | 2024-08-22
| 3610 | 3.3.0 Define Lecture and Exam Periods | 12 |  |  |  | 522 | 12.4286 | 2024-08-24
| 3620 | 3.5.0 Change Mode | 16 |  |  |  | 538 | 12.8095 | 2024-08-26 16:00
| 3710 | 3.10.1 Recording changes | 22 |  |  |  | 560 | 13.3333 | 2024-08-30 08:00
| 3990 | 3.0.1 It should be intuitive. | 10 |  |  |  | 570 | 13.5714 | 2024-09-01
| 3810 | 3.80.1 Go To Date | 20 |  |  |  | 590 | 14.0476 | 2024-09-04 08:00
| 3850 | 3.80.2 Select Number of Weeks | 20 |  |  |  | 610 | 14.5238 | 2024-09-07 16:00
| 3880 | 3.80.3 Filter | 40 |  |  |  | 650 | 15.4762 | 2024-09-14 08:00 | 3rd milestone
| 3950 | 3.222.2 Unforseen Issues | 30 |  |  |  | 680 | 16.1905 | 2024-09-19 08:00 | 2024-08-29
| 4100 | 4.10.0 Study Plans | 10 |  |  |  | 690 | 16.4286 | 2024-09-21
| 4110 | 4.10.1 Create Study Plan | 25 |  |  |  | 715 | 17.0238 | 2024-09-25 04:00
| 4120 | 4.10.2 Edit Study Plan | 7 |  |  |  | 722 | 17.1905 | 2024-09-26 08:00
| 4130 | 4.10.3 Delete Study Plan | 3 |  |  |  | 725 | 17.2619 | 2024-09-26 20:00
| 4140 | 4.10.4 Download Study Plans | 16 |  |  |  | 741 | 17.6429 | 2024-09-29 12:00
| 4150 | 4.10.5 Upload Study Plans | 16 |  |  |  | 757 | 18.0238 | 2024-10-02 04:00
| 4210 | 4.2.1 Downloading File | 5 |  |  |  | 762 | 18.1429 | 2024-10-03
| 4220 | 4.2.2 Human Readable Form | 5 |  |  |  | 767 | 18.2619 | 2024-10-03 20:00
| 4230 | 4.2.20 Saving Calendar | 5 |  |  |  | 772 | 18.381 | 2024-10-04 16:00
| 4310 | 4.20.0 Lecturers | 4 |  |  |  | 776 | 18.4762 | 2024-10-05 08:00
| 4320 | 4.20.1 Lecturers Collection | 4 |  |  |  | 780 | 18.5714 | 2024-10-06
| 4330 | 4.20.2 Lecturers Download | 4 |  |  |  | 784 | 18.6667 | 2024-10-06 16:00
| 4410 | 4.20.3 Lecturers Conflict Analysis | 25 |  |  |  | 809 | 19.2619 | 2024-10-10 20:00
| 4420 | 4.10.6 Study Plan Conflict Analysis | 80 |  |  |  | 889 | 21.1667 | 2024-10-24 04:00
| 4450 | 4.1.1 Show Conflicts | 40 |  |  |  | 929 | 22.119 | 2024-10-30 20:00
| 4800 | 4.3.0 Create Course | 4 |  |  |  | 933 | 22.2143 | 2024-10-31 12:00
| 4810 | 4.3.1 Creating an Appointment via button | 2 |  |  |  | 935 | 22.2619 | 2024-10-31 20:00
| 4820 | 4.3.2 Creating an Appointment via double click | 1 |  |  |  | 936 | 22.2857 | 2024-11-01
| 4830 | 4.3.3 Editing Appointment | 2 |  |  |  | 938 | 22.3333 | 2024-11-01 08:00
| 4840 | 4.3.4 Moving Appointment per Drag & Drop | 1 |  |  |  | 939 | 22.3571 | 2024-11-01 12:00
| 4850 | 4.3.5 Deleting Appointment | 1 |  |  |  | 940 | 22.381 | 2024-11-01 16:00
| 4860 | 4.3.6 Deleting All Appointments | 2 |  |  |  | 942 | 22.4286 | 2024-11-02
| 4870 | 4.1.1 Uploading File per Drag & Drop | 10 |  |  |  | 952 | 22.6667 | 2024-11-03 16:00
| 4880 | 4.1.2 Uploading File per File Selection | 10 |  |  |  | 962 | 22.9048 | 2024-11-05 08:00 | 4th milestone
| 4950 | 4.222.2 Unforseen Issues | 30 |  |  |  | 992 | 23.619 | 2024-11-10 08:00 | 2024-10-31
Formulas:
Date = TODAY()+7*[Weeks]

## Availability
Availability Planning & Schedule |  |  | minus orga time
1
Michael | 15 | h per week | 14
Alexander | 15 | h per week | 14
Mostafa | 15 | h per week | 14
|  |  |  | Hours | Needed weeks | Orga hours | Total hours | Date
Sum | 42 | h per week |  | 992 | 23.619 | 70.8571 | 1062.8571 | 2024-11-10 08:00
All according to credits | 30 | h per week |  | 1080 | 36 | 0 | 1080 | 2025-02-05
All according to credits | 45 | h per week |  | 1080 | 24 | 0 | 1080 | 2024-11-13
1st Milestone |  | 2024-05-16
2nd Milestone |  | 2024-06-27
3rd Milestone |  | 2024-08-29
4th Milestone |  | 2024-10-31
Acceptance Meeting |  | 2024-11-07
Formulas:
Date = TODAY()+7*[Needed weeks]

## Issues
Issues
Documentation (see instructions)
See questions

## Questions
Questions

## Links
Zoom Meeting
https://us05web.zoom.us/j/2067865496?pwd=ZjIzVll6YlIvbGdIdkR5VlVpNjVlZz09
Meeting-ID: 206 786 5496
Kenncode: aLa9in
BBB always open:
https://webconf.hrz.uni-marburg.de/n/rooms/myo-bbb-tt8-fsk/join
https://hessenbox.uni-marburg.de
Gitlab:
https://gitlab.uni-marburg.de/harry/service-pages
Bookable calendar of Prof. Bockisch
https://doodle.com/bp/christophbockisch/book-a-time
Example page
https://www.mathematik.uni-marburg.de/studium/preview/index.html